## USNStart Landing Page
GANTT CHART - USNStart Landing Page
PROJECT TITLE | USNStart Landing Page
PROJECT MANAGER
COMPANY NAME
DATE | 2024-02-05
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE | [14 empty] | PHASE SIX
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1.1 | Project planning and organizing
1.1.1 | Finding out our business idea | Henriette | 2024-01-01 | 2024-01-02 | 2 | 100%
1.1.2 | Project Charter Revisions |  | 2023-03-15 | 2024-01-03 | 295 | 100%
1.1.2 | Finding out what we want to offer | Sarina | 2024-01-02 | 2024-01-03 | 2 | 100%
1.1.3 | Coordination with project stakeholders for feedback and review | Hanne | 2024-01-03 | 2024-01-05 | 3 | 100%
1.1.4 | Clarify our objective and goals | Adam | 2024-01-08 | 2024-01-12 | 5 | 100%
1.1.5 | Putting schedules and checkpoints | Jenny | 2024-01-11 | 2024-01-12 | 2 | 100%
1.1.6 | Defining functional and non-functional requirements | Henriette | 2024-01-15 | 2024-01-19 | 5 | 100%
1.2 | Website development
1.2.1 | Defining website content | Adam | 2024-01-22 | 2024-01-26 | 5 | 50%
1.2.2 | Creating a responsive website layout and design | Hanne | 2024-01-25 | 2024-01-31 | 5 | 0%
1.2.3 | Accessibility on different devices (Desktop, mobile, tablet) | Sarina | 2024-02-01 | 2024-02-08 | 6 | 0%
1.2.4 | Server framework | Henriette | 2024-02-05 | 2024-02-09 | 5 | 0%
1.2.5 | Providing protection of users data | Jenny | 2024-02-05 | 2024-02-09 | 5 | 0%
1.2.6 | Fulfilling all functional and non-functional requirements | Hanne | 2024-02-08 | 2024-02-09 | 2 | 0%
1.3 | Website content
1.3.1 | Making Membership plans | Adam | 2024-02-07 | 2024-02-12 | 4 | 0%
1.3.2 | Providing detailed information about what we offer | Sarina | 2024-02-12 | 2024-02-16 | 5 | 0%
1.3.3 | Providing key information | Henriette | 2024-02-12 | 2024-02-16 | 5 | 0%
1.3.4 | Provide a booking system for members | Hanne | 2024-02-19 | 2024-02-23 | 5 | 0%
1.3.5 | Providing customer support and communication channel (email) | Jenny | 2024-02-26 | 2024-03-01 | 5 | 0%
1.3.6 | Adding videos and images that enhances user experience and information flow | Sarina | 2024-02-28 | 2024-03-01 | 3 | 0%
1.4 | Testing
1.4.1 | Testing functionality and quality across all platforms | Hanne | 2024-03-04 | 2024-03-11 | 6 | 0%
1.4.2 | Testing user data security | Adam | 2024-03-08 | 2024-03-15 | 6 | 0%
1.4.3 | Testing to identify problems or bugs | Henriette | 2024-03-14 | 2024-03-22 | 7 | 0%
1.5 | Finishing project
1.5.1 | Finalizing the project | Jenny | 2024-03-25 | 2024-03-29 | 5 | 0%
1.5.2 | Taking feedback | Hanne | 2024-03-25 | 2024-04-04 | 9 | 0%
1.5.3 | Evaluating results from testing | Sarina | 2024-03-27 | 2024-04-04 | 7 | 0%
1.5.4 | Making sure all previous checkpoints are met | Henriette | 2024-04-08 | 2024-04-16 | 7 | 0%
1.5.5 | Consulting with stakeholders | Adam | 2024-04-08 | 2024-04-16 | 7 | 0%
1.5.6 | Deploying website live | Jenny | 2024-04-17 | 2024-04-19 | 3 | 0%
1.6 | Maintenance
1.6.1 | Continuous adjustments and improvements based on user inputs | Hanne | 2024-04-22 | 2024-05-10 | 15 | 0%
1.6.2 | Technical updates | Adam | 2024-05-06 | 2024-05-10 | 5 | 0%