## USNStart Landing Page
GANTT CHART - USNStart Landing Page
PROJECT TITLE | USNStart Landing Page
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | Januar |  | Februar |  |  |  | Mars |  |  |  | April
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | 15 | 31 | 1 | 10 | 20 | 29 | 2 | 10 | 20 | 31 | 1 | 10 | 20 | 30
1.1 | Sprint 0 - Project management
1.1.1 | Establish Team | Henriette | 2024-01-15 | 2024-01-30 | 16 | 100%
1.1.2 | Project Charter Revisions |  | 2023-03-15 | 2024-01-03 | 295 | 100%
1.1.2 | Defining Project Scope | Sarina | 2024-01-18 | 2024-01-31 | 14 | 100%
1.1.3 | Develop Project Charter | Hanne | 2024-01-22 | 2024-02-05 | 15 | 100%
1.1.4 | User stories | Adam | 2024-01-22 | 2024-02-05 | 15 | 100%
1.1.5 | Clarify our objective and goals | Jenny | 2024-01-29 | 2024-02-05 | 8 | 100%
1.1.6 | Milestone 1 | All | 2024-01-15 | 2024-02-05 | 22 | 100%
1.2 | Sprint 1
1.2.1 | Planning | Adam | 2024-02-06 | 2024-02-16 | 11 | 100%
1.2.2 | Design | Hanne | 2024-02-06 | 2024-02-16 | 11 | 100%
1.2.3 | Development | Sarina | 2024-02-06 | 2024-03-01 | 25 | 100%
1.2.4 | Testing | Jenny | 2024-02-06 | 2024-03-01 | 25 | 100%
1.2.5 | Review | Hanne | 2024-03-01 | 2024-03-04 | 4 | 100%
1,2.6 | Milestone 2 | All | 2024-02-06 | 2024-03-04 | 28 | 100%
1.3 | Sprint 2
1.3.1 | Planning | Henriette | 2024-03-05 | 2024-03-15 | 11 | 100%
1.3.2 | Design | Hanne | 2024-03-05 | 2024-03-15 | 11 | 100%
1.3.3 | Development | Hanne | 2024-03-05 | 2024-04-01 | 28 | 100%
1.3.4 | Testing | Adam | 2024-03-05 | 2024-04-01 | 28 | 100%
1.3.5 | Review | Sarina | 2024-04-01 | 2024-04-03 | 3 | 100%
1.3.6 | Milestone 3 | All | 2024-03-05 | 2024-04-03 | 30 | 100%
1.4 | Sprint 3
1.4.1 | Planning | Henriette | 2024-04-04 | 2024-04-12 | 9 | 0%
1.4.2 | Design | Jenny | 2024-04-04 | 2024-04-12 | 9 | 0%
1.4.3 | Development | Hanne | 2024-04-04 | 2024-04-19 | 16 | 0%
1.4.4 | Testing | Adam | 2024-04-04 | 2024-04-19 | 16 | 0%
1.4.5 | Review | Henriette | 2024-04-19 | 2024-04-20 | 2 | 0%
1.5 | Completion
1.5.1 | Final product testing | Sarina | 2024-04-20 | 2024-04-27 | 8 | 0%
1.5.2 | Bug fixing | Hanne | 2024-04-20 | 2024-04-27 | 8 | 0%
1.5.3 | Documentation | Henriette | 2024-04-20 | 2024-04-27 | 8 | 0%
1.5.4 | Project review meeting | All | 2024-04-27 | 2024-04-27 | 1 | 0%
1.5.5 | Final project plan delivery | All | 2024-04-28 | 2024-04-30 | 3 | 0%